## Sheet1
ID | Work Name | Duration by single worker | manhour | Type of Worker | Minimum Required Number of Workers | Location | Max. Number of Workers
1 | Wall Stud Installation | 40 | 40 | Sheet Steel Worker | 2 | Inside | 4
2 | Install Insulator to Steel Frame | 30 | 30 | Construction Labor | 1 | Outside | 4
3 | Install Door and Window Frame (Short Side) | 40 | 40 | Window Framer | 2 | Outside | 4
4 | Install Pipe Shaft Frame | 10 | 10 | Metal Worker | 1 | Outside | 4
5 | Corner Floor Concrete Pouring | 10 | 10 | Construction Labor | 1 | Inside | 4
6 | Install Fire and Water Proof Gypsum Board to Inside Wall (Long Side) | 20 | 20 | Joiner | 2 | Inside | 4
7 | Install Fire Proof Gypsum Board to Inside Wall (Long Side) | 140 | 140 | Joiner | 2 | Inside | 4
8 | Install Insulator(Glass Wool) to Wall(Long Side) | 60 | 60 | Construction Labor | 2 | Outside | 4
9 | Install Electric Power Distribution Cabinet (Short Side) | 5 | 5 | Electricians | 1 | Inside | 4
10 | Install Wall Pipe (Short Side) | 10 | 10 | Pipefitter | 1 | Inside | 4
11 | Fix Wall Pipe (Long Side) | 10 | 10 | Pipefitter | 1 | Inside | 4
12 | Install Wall Pipe (Long Side) | 20 | 20 | Pipefitter | 1 | Inside | 4
13 | Install Gypsum Board to Inside Wall (Short Side) | 80 | 80 | Joiner | 2 | Inside | 4
14 | Install Cement Board (Long Side) | 40 | 40 | Joiner | 2 | Outside | 4
15 | Inside Stud Installation (Bath Room) | 10 | 10 | Joiner | 1 | Inside | 4
16 | Install Insulator(Glass Wool) to Wall(Long Side) | 60 | 60 | Construction Labor | 2 | Outside | 4
17 | Install Insulator(Glass Wool) to Wall(Short Side) | 30 | 30 | Construction Labor | 1 | Outside | 4
18 | Install Cement Board (Long Side) | 40 | 40 | Joiner | 2 | Outside | 4
19 | Install Insulator to Inside Wall | 10 | 10 | Joiner | 1 | Inside | 4
20 | Install Pipe in Pipe Shaft Frame | 80 | 80 | Pipefitter | 2 | Inside | 4
21 | Install Power Outlet Box and Electric Wire | 20 | 20 | Electricians | 2 | Inside | 4
22 | Install Lighting and Outlet Socket | 60 | 60 | Electricians | 2 | Inside | 4
23 | Install Stiffening Plate for Fixing Sanitary Fixture in Bathroom | 10 | 10 | Joiner | 1 | Inside | 2
24 | Wrap Water Proof Paper (Long Side) | 40 | 40 | Joiner | 2 | Outside | 4
25 | Install Water Proof Gypsum Board to Bathroom | 80 | 80 | Joiner | 2 | Inside | 2
26 | Install Cement Board (Short Side) | 40 | 40 | Joiner | 2 | Outside | 4
27 | Install Gypsum Board to Inside Wall (Short Side) | 40 | 40 | Joiner | 2 | Inside | 4
28 | Wrap Water Proof Paper (Long Side) | 40 | 40 | Joiner | 2 | Outside | 4
29 | Install Outlet Socket (Short Aisle Side) | 20 | 20 | Electricians | 2 | Outside | 4
30 | Install Door | 60 | 60 | Metal Worker | 2 | Outside | 4
31 | Install Window | 20 | 20 | Window Framer | 2 | Outside | 4
32 | Putty Inside Wall | 30 | 30 | Painter | 1 | Inside | 4
33 | Electric Wiring in Ceiling | 60 | 60 | Electricians | 2 | Inside | 4
34 | Install Pipe Shaft Frame Door | 20 | 20 | Metal Worker | 2 | Outside | 4
35 | Transport Steel Frame for Fixing Exterior Wall Panel Bracket | 5 | 5 | Metal Worker | 1 | Outside | 4
36 | Fix the Steel Frame for Exterior Wall Panel | 40 | 40 | Metal Worker | 2 | Outside | 4
37 | Lighting and Outlet Socket Wiring | 40 | 40 | Electricians | 2 | Outside | 4
38 | Install Hanger Bolt for Suspended Ceiling | 40 | 40 | Joiner | 2 | Inside | 4
39 | Install Curtain Box | 40 | 40 | Joiner | 2 | Inside | 4
40 | Install Carrying Channel for Suspended Ceiling | 20 | 20 | Joiner | 2 | Inside | 4
41 | Install Minor Channel for Suspended Ceiling | 20 | 20 | Joiner | 2 | Inside | 4
42 | Install M-bar for Suspended Ceiling | 40 | 40 | Joiner | 2 | Inside | 4
43 | Install Outlet Socket Cover (Short Aisle Side) | 5 | 5 | Electricians | 1 | Outside | 4
44 | Install Gypsum Board to Ceiling | 120 | 120 | Joiner | 2 | Inside | 4
45 | Wrapping Modular Unit | 60 | 60 | Joiner | 2 | Inside | 4